## Sheet1
Table 4. PPI Projects and Initiatives
Outreach Projects (OP)
Target Audience | Message(s) (See Table 4) | Outcome (See Table 4) | Project(s) | Assignment | Schedule | Stakeholder
1. All properties in the City | A - F, H | A - F, H | OP 1. Pasadena Now articles | City Communication Office | One article in each newsletter on a message | N/A (City is sponsor)
|  |  | OP 2. Facebook and Twitter messages | City Communication Office | One message sent out monthly on a new topic
|  |  | OP 3. Handouts on the messages | City Communication Office | Distribute to various City offices for display
|  |  | OP 4. Handouts on the messages | City Communication Office | Distribute to various stakeholder locations for their displays and handouts | Armand Bayou Nature Center
Chamber of Commerce
Insurance agencies
|  |  | OP 5. Booths at city-wide festivals | City Environmental Svcs Coordinator | February Business Expo | Chamber of Commerce
[5 empty] | March Trash Bash | Galveston Bay Foundation
[5 empty] | May Strawberry Festival | San Jacinto Day Foundation
[5 empty] | June Hurricane Workshop | SER LEPC
October Neighborhood network convention
[5 empty] | Fall Festival (November) | Armand Bayou Nature Center
|  |  | Map inquiry service | City Engineering | Year-round as part of regular service
|  |  | City, Flood Control District, and LEPC websites | City Communication Office | Year-round as part of regular service
| B. You need flood insurance, I. Everyone can get flood insurance | B | OP 6. Insurance agents | Insurance agencies | Discussions with clients as they happen | Insurance agencies
| F. Only rain goes down the drain | F | OP 7. Presentations on protecting the waterways | Armand Bayou Nature Center | Include as part of all presentations (one each month to different groups) | Armand Bayou Nature Center
|  |  |  | Galveston Bay Foundation |  | Galveston Bay Foundation
|  |  | OP 8. Storm drain stenciling | City Public Works Adopt a Waterway program | Year-round
| H. Protect your house | H | OP 9. Guidebook | City Environmental Svcs Coordinator | At displays and provided at all meetings
| E. Get a permit, G. Know the flood protection construction rules | E, G | OP 10. Permit handouts | City Building Department | Handouts provided at permit counter and at all meetings
2. Repetitive loss areas | A - F, H | A - F, H | OP 11. Repetitive loss mailing | City Environmental Svcs Coordinator | Annual mailing that covers all the topics, tailored for repetitive flooding
| A - I | A - I | OP 12. Presentations to neighborhood associations | City Environmental Svcs Coordinator | Presentations on flood protection to neighborhood associations or meetings of repetitive loss area residents | Neighborhood associations
3. Spanish speakers | A - F, H, I | A - F, H, I | OP 13. Handouts in Spanish | City Communication Office | OP 3 handouts translated into Spanish and distributed together | Same as OP 3 and OP 4
|  |  | OP 9. Guidebook in Spanish | City Environmental Svcs Coordinator (speaks Spanish) | At displays and provided at all meetings
|  |  | OP 5. Booth | City Environmental Svcs Coordinator | November Hispanic Fest
|  |  | OP 6. Insurance agents | Spanish speaking insurance agencies | Discussions with clients as they happen | Spanish speaking insurance agencies
|  |  | OP 12. Bilingual presentations to neighborhood associations | City Environmental Svcs Coordinator (speaks Spanish) | Presentations on flood protection to neighborhood associations or meetings of repetitive loss area residents | Hispanic neighborhood associations
4. Landscapers | E. Get a permit, G. Construction rules | E, G | OP 13. Presentation at Neighborhood Network association meeting | Cleveland-Ripley Neighborhood Center | Schedule meeting with association by February 15 | Cleveland-Ripley Neighborhood Association
5. Builders | E. Get a permit, G. Construction rules, H. Protect your house | E, G, H | OP 14. Presentation at Habitat for Humanity Contractor’s meeting | City Building Department | Schedule meeting with Habitat from Humanity Contractor by February 15 | Habitat for Humanity Contractors
6. Real estate, lenders, insurance | A. Know risk, B. Insurance, E. get a permit, I. Everyone can get flood insurance | A, B, E, I | OP 15. Mailing on City services, including relevant OP 4 handouts | City Environmental Svcs Coordinator | Mailing to go out by February 15
Flood Response Projects (FRP)
1. All properties in the City | A. Know risk, C. Turn around | A, C | FRP 1. Press Release (TV, Radio, Facebook) | City Communication Office | Release at first flood notice
|  |  | FRP 2. Flyer : “Preparing Make Sense, Get Ready Now” | City Communication Office | Release at first flood notice
|  |  | FRP 3. Mayor’s Notification release | City Communication Office, Mayor | Release at first flood notice
|  |  | Website and SMS communication system (Cell phone alarm) text message information | City Communication Office | Draft and upload by February 15
| G. Know the flood protection reconstruction rules | G | FRP 4. Handouts for City staff to distribute when in the field | City Communication Office | Distribute when staff in field following a flood
3. Spanish speakers | A. Know risk, C. Turn around | A, C | FRP 2 Flyers translated into Spanish | City Environmental Svcs Coordinator (speaks Spanish) | Release at first flood notice | Hispanic neighborhood associations (on their letterhead)
| G. Know the reconstruction rules | G | FRP 4. Handouts translated into Spanish | City Communication Office | Distribute when staff in field following a flood | Hispanic neighborhood associations (on their letterhead)